## Summary
HVAC Change Order Calculator Summary
Indicator | Calculated Value | Entered Status | Count
Change orders entered |  | Draft
Total direct cost |  | Pending review
Original allowance total |  | Approved
Calculated change price |  | Declined
Approved and completed value |  | Completed
Pending review value
Average entered price
Rows flagged for human check
Credits or negative values
Earliest entered date
Latest entered date

## Change Orders
HVAC Change Order Calculator
Enter scope and pricing inputs in light orange cells. Review flags request a human check.
Change Order ID | Date | Customer | Job | Equipment | Technician | Description | Quantity | Unit | Labor Hours | Labor Rate Override | Material Unit Cost | Other Cost | Original Allowance | Markup % Override | Taxable Cost | Tax Rate Override | Responsibility | Status | Labor Cost | Material Cost | Direct Cost | Allowance Variance | Markup Amount | Tax Amount | Change Order Price | Review Alert
DEMO-CO-26-001 | 2025-09-12 | Bluebird Demo Market (Fictional) | Bluebird Demo Remodel (Fictional) | RTU-1 Demo Asset (7.5 ton) | Casey Sample (Fictional) | Add 18 feet of insulated supply duct after a fictional layout revision. | 18 | ft | 6.5 |  | 80 | 180 | 900 |  | 1620 |  | Customer request | Pending review
DEMO-CO-26-002 | 2025-10-27 | Cedar Lane Sample Offices (Fictional) | Cedar Lane Sample Suite (Fictional) | AHU-2 Demo Asset (5 ton) | Morgan Example (Fictional) | Relocate one demo thermostat after a partition location changed. | 1 | each | 3 | 105 | 275 | 0 | 0 | 12% | 275 | 0% | Design clarification | Approved
DEMO-CO-26-003 | 2025-12-16 | Northstar Test Kitchen (Fictional) | Northstar Test Kitchen Fit-Out (Fictional) | MAU-1 Demo Asset (2,500 CFM) | Riley Demo (Fictional) | Add a fictional crane rescheduling charge after site access changed. | 1 | lot | 4 |  | 0 | 900 | 500 |  | 900 |  | Customer request | Draft
DEMO-CO-26-004 | 2026-02-04 | Juniper Mock Library (Fictional) | Juniper Mock Reading Room (Fictional) | VAV-3 Demo Asset (1,200 CFM) | Taylor Placeholder (Fictional) | Add two return grilles for the fictional revised ceiling plan. | 2 | each | 5.5 |  | 320 | 50 | 400 |  | 690 |  | Design clarification | Completed
DEMO-CO-26-005 | 2026-03-16 | Copper Kettle Demo Cafe (Fictional) | Copper Kettle Demo Addition (Fictional) | HP-2 Demo Asset (3 ton) | Casey Sample (Fictional) | Upgrade the fictional heat pump selection after the requested scope expanded. | 1 | each | 12 |  | 4200 | 350 | 3600 | 18% | 4550 |  | Customer request | Pending review
DEMO-CO-26-006 | 2026-04-25 | Maple Stage Sample Theater (Fictional) | Maple Stage Sample Renovation (Fictional) | CU-4 Demo Asset (4 ton) | Morgan Example (Fictional) | Replace 35 feet of demo refrigerant line after fictional handling damage. | 35 | ft | 8 |  | 20 | 0 | 2000 |  | 700 |  | Contractor correction | Declined
DEMO-CO-26-007 | 2026-06-04 | Sunset Prototype Studios (Fictional) | Sunset Prototype Studio B (Fictional) | FCU-5 Demo Asset (18,000 Btu/h) | Riley Demo (Fictional) | Add one condensate pump after a fictional drain routing conflict was found. | 1 | each | 2 |  | 190 | 25 | 0 |  | 215 |  | Unforeseen condition | Approved
DEMO-CO-26-008 | 2026-07-14 | Willow Creek Demo Clinic (Fictional) | Willow Creek Demo Wing (Fictional) | DUCT-6 Demo Asset (Main Trunk) | Taylor Placeholder (Fictional) | Revise the fictional air distribution route around a concealed beam. | 1 | lot | 40 |  | 2300 | 1200 | 1500 |  | 3500 |  | Unforeseen condition | Pending review
DEMO-CO-26-009 | 2026-08-23 | Orchard Sample Apartments (Fictional) | Orchard Sample Unit 12 (Fictional) | EF-7 Demo Asset (300 CFM) | Casey Sample (Fictional) | Document a fictional no-cost equipment label revision. | 1 | each | 0 |  | 0 | 0 | 0 | 0% | 0 | 0% | Original allowance | Completed
DEMO-CO-26-010 | 2026-09-12 | Harborlight Demo Workshop (Fictional) | Harborlight Demo Expansion (Fictional) | AHU-8 Demo Asset (10 ton) | Morgan Example (Fictional) | Add a demo air handler and revised duct package after a fictional scope expansion. | 1 | lot | 40.5 | 120 | 12000 | 2500 | 2000 | 15% | 14500 | 8% | Customer request | Draft

## Assumptions
Editable Assumptions and Lists
Setting | Editable Value | Unit Choices | Technician Choices | Responsibility Choices | Status Choices
Default labor rate | 95 | each | Casey Sample (Fictional) | Customer request | Draft
Default markup | 15% | ft | Morgan Example (Fictional) | Contractor correction | Pending review
Default sales tax rate | 7.25% | inch | Riley Demo (Fictional) | Unforeseen condition | Approved
Labor hours review threshold | 40 | lb | Taylor Placeholder (Fictional) | Design clarification | Declined
Earliest allowed change date | 2025-09-12 | lot |  | Original allowance | Completed
Latest allowed change date | 2027-09-12 | hour
Absolute price review threshold | 15000 | ton
Minimum markup input | -100%
Maximum markup input | 500%
Maximum tax rate input | 100%
Use Notes
Defaults | Blank rate overrides use the editable defaults above. Enter an override only when the specific estimate requires one.
Tax inputs | Tax rate and taxable cost are planning inputs. Verify the treatment for the specific fictional job before use.
Review prompts | Review flags request a human check and do not indicate approval, engineering acceptance, or official status.
Sample data | All sample customers, jobs, assets, technicians, and transactions in this workbook are fictional.