## Summary
HVAC Job Costing Summary
Indicators use only entered job data. All sample customers, technicians, equipment, and jobs are fictional. |  |  |  | Workbook date | 2026-09-11
Cost and Margin Indicators |  |  | Job Status
Jobs entered |  |  | Draft
Estimated cost |  |  | Scheduled
Quoted revenue |  |  | In Progress
Actual cost recorded |  |  | Complete
Actual revenue recorded |  |  | On Hold
Recorded gross margin
Recorded gross margin %
Cost alert jobs
Low-margin jobs
Cost Category | Estimated | Actual
Labor
Material
Equipment
Subcontract
Overhead

## Job Costing
HVAC Job Costing Detail
Compare estimated and actual costs, revenue, and margin for each fictional demonstration job.
Enter data in orange cells. Alerts identify records that need human review.
Job ID | Customer | Job Description | Equipment | Lead Technician | Start Date | Quantity | Unit | Cost Responsibility | Status | Est. Labor Hours | Est. Labor Rate | Est. Labor Cost | Est. Material Cost | Est. Equipment Cost | Est. Subcontract Cost | Est. Overhead | Est. Total Cost | Quoted Price | Actual Labor Hours | Actual Labor Rate | Actual Labor Cost | Actual Material Cost | Actual Equipment Cost | Actual Subcontract Cost | Actual Overhead | Actual Total Cost | Actual Revenue | Cost Variance | Labor Hours Variance | Revenue Variance | Gross Margin | Gross Margin %
DEMO-J001 | Fictional Copper Finch Cafe | Replace packaged cooling and heating unit | Demo 5-ton packaged unit | Fictional Tech Blair | 2026-06-11 | 1 | system | Contractor | Complete | 28 |  |  | 1450 | 8200 | 650 |  |  | 17250 | 30 |  |  | 1550 | 8250 | 700 |  |  | 17250
DEMO-J002 | Fictional Lantern Workshop | Perform seasonal service on split systems | Demo split systems | Fictional Tech Avery | 2026-06-23 | 4 | unit | Contractor | Complete | 10 |  |  | 280 | 0 | 0 |  |  | 1300 | 9.5 |  |  | 260 | 0 | 0 |  |  | 1300
DEMO-J003 | Fictional Maple Kite Offices | Replace air handler motor | Demo 7.5-ton air handler | Fictional Tech Casey | 2026-07-07 | 1 | system | Contractor | Complete | 12 |  |  | 380 | 1950 | 0 |  |  | 3600 | 13 |  |  | 425 | 2025 | 0 |  |  | 3600
DEMO-J004 | Fictional Silver Acorn Market | Repair refrigerant piping | Demo walk-in cooler condensing unit | Fictional Tech Devon | 2026-07-19 | 45 | linear foot | Shared | Complete | 18 |  |  | 1150 | 300 | 850 |  |  | 4100 | 20 |  |  | 1280 | 325 | 900 |  |  | 4000
DEMO-J005 | Fictional Paper Moon Studio | Install ductless heat pump | Demo 2-zone ductless system | Fictional Tech Ellis | 2026-08-01 | 2 | zone | Contractor | Complete | 24 |  |  | 920 | 5100 | 500 |  |  | 9800 | 23 |  |  | 880 | 5075 | 500 |  |  | 9800
DEMO-J006 | Fictional Juniper Clock School | Provide replacement filter kit | Demo rooftop filter bank | Fictional Tech Avery | 2026-08-13 | 12 | unit | Customer | Complete | 0 |  |  | 480 | 0 | 0 |  |  | 750 | 0 |  |  | 460 | 0 | 0 |  |  | 750
DEMO-J007 | Fictional Harbor Quilt Hall | Replace supply fan assembly | Demo rooftop supply fan | Fictional Tech Casey | 2026-08-26 | 1 | unit | Contractor | In Progress | 16 |  |  | 600 | 2300 | 0 |  |  | 4500 | 8 |  |  | 300 | 2200 | 0
DEMO-J008 | Fictional Cobalt Umbrella Gym | Diagnose comfort complaint | Demo variable-air-volume zone | Fictional Tech Devon | 2026-09-04 | 1 | zone | Contractor | In Progress | 6 |  |  | 150 | 0 | 0 |  |  | 850 | 5.5 |  |  | 80 | 0 | 0
DEMO-J009 | Fictional Peach Compass Clinic | Replace condensing unit | Demo 4-ton condensing unit | Fictional Tech Blair | 2026-09-18 | 1 | system | Contractor | Scheduled | 20 |  |  | 700 | 3900 | 350 |  |  | 7900
DEMO-J010 | Fictional Meadow Rocket Apartments | Clean common-area duct sections | Demo common-area duct system | Fictional Tech Ellis | 2026-09-26 | 180 | linear foot | Shared | Draft | 32 |  |  | 950 | 450 | 1200 |  |  | 6200

## Assumptions
HVAC Job Costing Assumptions
Orange cells are editable. Rates and alert limits are planning assumptions, not guaranteed prices or requirements.
Operating Assumption | Value | Technician | Burdened Labor Cost | Status Choices | Responsibility Choices | Unit Choices
Overhead rate on direct cost | 10% | Fictional Tech Avery | 42 | Draft | Contractor | job
Gross margin warning threshold | 20% | Fictional Tech Blair | 45 | Scheduled | Customer | system
Cost variance alert amount | 250 | Fictional Tech Casey | 48 | In Progress | Shared | zone
Maximum labor hours per job | 1000 | Fictional Tech Devon | 43 | Complete |  | unit
Maximum cost or price entry | 1000000 | Fictional Tech Ellis | 50 | On Hold |  | linear foot
Maximum quantity per job | 1000