## Summary
Fictional Northstar HVAC — Work Order Summary
As of
Open work orders |  | Ready to bill | Review flags
Total price |  | Total cost | Labor hours
Completed |  | Unbilled price | Assigned or scheduled
Work Status | Count

## Work Orders
Fictional Northstar HVAC — Work Order Tracker
Enter work details in peach cells. Review prompts call for a human check and do not perform outside actions.
Work Order ID | Customer | Equipment | Technician | Request Date | Service Date | Completion Date | Service or Parts Description | Quantity | Unit | Labor Hours | Material Cost | Labor Cost | Total Cost | Price | Responsibility | Work Status | Billing Status | Review
FWO-26-001 | Fictional Juniper Learning Lab | Demo RTU-01, 5-ton rooftop unit | Fictional Avery Reed | 2026-08-08 | 2026-08-10 | 2026-08-10 | Replace two demo 20 x 25 x 2 in. filters and test operation | 2 | each | 2.25 | 78 |  |  | 460 | Customer | Completed | Billed
FWO-26-002 | Fictional Copper Kettle Cafe | Demo AHU-02, 3-ton air handler | Fictional Jordan Pike | 2026-08-31 | 2026-09-02 | 2026-09-02 | Replace demo condensate pump and verify drainage | 1 | each | 1.5 | 96 |  |  | 320 | Customer | Completed | Ready to Bill
FWO-26-003 | Fictional Paper Airplane Studio | Demo HP-03, 36,000 Btu/h heat pump | Fictional Morgan Vale | 2026-09-08 | 2026-09-11 |  | Continue demo refrigerant circuit service; record 2 lb used | 2 | lb | 3.25 | 190 |  |  | 690 | Customer | In Progress | Not Ready
FWO-26-004 | Fictional Moonbeam Market | Demo FCU-04, fan-coil unit | Fictional Casey Flint | 2026-08-21 | 2026-08-23 |  | Diagnose airflow issue; demo fan motor remains pending | 0 | each | 2 | 0 |  |  | 240 | Contractor | Waiting on Parts | Not Ready
FWO-26-005 | Fictional Blue Door Workshop | Demo RTU-05, 7.5-ton rooftop unit | Fictional Riley Snow | 2026-09-09 | 2026-09-14 |  | Scheduled maintenance with one demo belt set | 1 | kit |  |  |  |  | 285 | Customer | Scheduled | Not Ready
FWO-26-006 | Fictional Acorn Pet Lodge | Demo furnace-06, 80,000 Btu/h | Fictional Taylor Cove | 2026-09-11 |  |  | Inspect intermittent demo furnace shutdown | [7 empty] | Customer | Assigned | Not Ready
FWO-26-007 | Fictional Kite String Offices | Demo mini-split-07, 24,000 Btu/h |  | 2026-09-12 |  |  | Review fictional comfort complaint and assign technician | [7 empty] | Customer | Requested | Not Ready
FWO-26-008 | Fictional Sunset Model Homes | Demo thermostat-08 |  | 2026-08-28 |  |  | Canceled fictional thermostat orientation request | 0 | service | 0 | 0 |  |  | 0 | No Charge | Canceled | No Charge
FWO-26-009 | Fictional Pebble Creek Theater | Demo boiler-09, 120,000 Btu/h | Fictional Avery Reed | 2026-09-04 | 2026-09-05 | 2026-09-05 | Replace one demo ignition control under fictional warranty | 1 | each | 2.5 | 210 |  |  | 0 | Warranty | Completed | No Charge
FWO-26-010 | Fictional Lantern Book Nook | Demo condenser-10, 4-ton unit | Fictional Jordan Pike | 2026-09-07 | 2026-09-10 | 2026-09-10 | Replace 18 ft of demo control wire and test operation | 18 | ft | 1.75 | 72 |  |  | 390 | Customer | Completed | Not Ready

## Assumptions
Fictional Northstar HVAC — Work Order Assumptions
Peach cells are editable planning inputs used by formulas, validations, and review prompts.
Review Setting | Value | How It Is Used | Technician | Labor Rate per Hour | Work Status | Unit | Responsibility | Billing Status
Open-age review days | 14 | Prompts a check for unfinished work older than this limit. | Fictional Avery Reed | 112 | Requested | each | Customer | Not Ready
Minimum price-to-cost margin | 20% | Prompts a price and cost review for customer-responsible work. | Fictional Jordan Pike | 118 | Assigned | ft | Contractor | Ready to Bill
Maximum quantity or labor entry | 10000 | Upper entry limit for quantity and labor hours. | Fictional Morgan Vale | 105 | Scheduled | lb | Warranty | Billed
Maximum cost or price entry | 1000000 | Upper entry limit for cost and price fields. | Fictional Casey Flint | 121 | In Progress | gal | No Charge | No Charge
Earliest entry date | 2020-01-01 | Earliest date accepted in the work order table. | Fictional Riley Snow | 110 | Waiting on Parts | kit
Latest entry date | 2100-12-31 | Latest date accepted in the work order table. | Fictional Taylor Cove | 115 | Completed | service
Maximum hourly labor rate | 1000 | Upper entry limit for technician labor rates. |  |  | Canceled
Use note | Review all rates, limits, dates, prices, and responsibilities before using this workbook.